LE3 Growth Portfolio

Pilot Plan

Spring/Summer 2026 • National Louis University

# Purpose

This document describes the specific plan for piloting the LE3 Growth Portfolio with real students and coaches at NLU. The pilot validates the tool’s core hypothesis: that AI-guided reflective conversations can help students develop self-awareness of their durable skills, and that the resulting data can be synthesized into compelling evidence of growth.

The pilot is structured in two phases: a controlled test with a single cohort, followed by an expanded deployment across multiple courses.

# Controlled Pilot

| Parameter | Detail |
| --- | --- |
| Duration | 4–6 weeks |
| Participants | Minimum of 1 coach, 5–10 students |
| LLM Provider | Gemini (via NLU Google contract) with Claude as fallback |
| Goal | Validate conversation quality, skill tag accuracy, and student engagement |

## Setup Checklist

### Infrastructure

- Set LLM_PROVIDER=gemini and GOOGLE_API_KEY in Vercel environment variables

- Insert pilot coach record into database with their real @nlu.edu email

- Configure Supabase Auth: customize magic link email template with NLU branding

- Add production Vercel URL to Supabase Auth redirect URLs whitelist

- Verify student-work storage bucket exists in Supabase Storage

- Create .env.example file documenting all required environment variables

### Course Setup

- Coach imports CSV via /work/import — system auto-tags each assignment with skills

- Coach reviews auto-generated skill tags, manually adjusts any incorrect ones

- Coach tests the full conversation flow with a sample assignment (end-to-end)

- Prepare student onboarding email with sign-in link and brief instructions

### Student Onboarding

- Send onboarding email to pilot students

- Students sign in via magic link → complete onboarding form (name, NLU ID, select coach)

- Students see their conversation hub with imported assignments grouped by skill

- Students complete their first conversation (guided walkthrough if needed)

## Weekly Cadence (Weeks 1–4+)

| Who | Weekly Activities |
| --- | --- |
| Students | Complete 1–2 conversations per week (10 min each). Submit new work or create open reflections. Review and confirm/edit skill tags on completed conversations. |
| Coach | Review 2–3 completed conversations per student. Provide SDT level assessments in the system. Use session prep before coaching meetings. Note where AI synthesis aligns/misaligns with their assessment. |
| Tech Lead | Monitor Vercel function logs for errors. Check LLM costs in Gemini/Anthropic dashboard. Review conversation quality samples. Address any reported issues. |

## What to Measure

| Metric | Target | How to Measure |
| --- | --- | --- |
| Conversation completion rate | 80%+ of started conversations reach synthesis | DB query: completed / (completed + abandoned + in_progress) |
| Time per conversation | 5–12 minutes average | duration_seconds field on completed conversations |
| Conversations per student per week | 1–2 | Count per student per week from started_at |
| Skill tag accuracy | 70%+ agreement with coach | Compare auto-tags vs coach assessments; track student tag edits |
| Student tag edits | Track volume and direction | Count confirms, removes, and student-added tags per conversation |
| Question specificity | Questions reference actual work content | Coach qualitative review of Phase 1 questions |
| Response depth | 50+ words average per phase | Character count of response_phase_1/2/3 fields |
| Student sentiment | 7+/10 on “valuable for growth” | Brief survey after 3+ conversations (Google Form) |
| Technical issues | Zero critical blockers | Vercel logs, student/coach reports |
| Skill coverage distribution | No skill with 0 conversations | Coverage query across all 12 skills |

## Decision Points

| Week | Decision | Criteria |
| --- | --- | --- |
| Week 2 | Continue or adjust? | If completion rate < 50% or sentiment < 5/10, pause and diagnose. Likely issue: question quality or conversation length. |
| Week 4 | Expand to Phase 2? | If completion > 80%, sentiment > 7/10, tag accuracy > 70%, and zero critical blockers → proceed to Phase 2. |
| Week 4 | Generate narratives? | If students have 3+ conversations per skill → generate narratives and get student feedback on accuracy. |

## Additional Metrics

- Narrative accuracy: Do students recognize themselves in the generated narratives? (survey)

- Narrative actionability: Can students use the career output in real applications?

- Coach time savings: Does session prep reduce preparation from 15 min to 5 min per student?

- Cross-course coherence: Do skill tags from different courses create a coherent picture?

- SDT progression: Can we observe level changes across the quarter?

- C2A data quality: Is the structured output useful for quantitative analysis?

## Success Criteria

- Students can articulate their growth using portfolio language in conversations and writing

- Coaches report measurable time savings and better-prepared sessions

- Narratives rated as “accurate” or “mostly accurate” by 75%+ of students

- System handles 50 concurrent users without performance degradation

- Skill tag accuracy exceeds 75% agreement with coach assessment

- At least 3 students use career output in real job/internship applications

# Risks and Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Low student engagement | Students treat conversations as busywork. Completion rates drop after week 1. | Keep conversations under 10 minutes. Let students choose which assignments to reflect on. Show immediate value via portfolio visualization. Consider gamification elements. |
| Poor question quality | LLM asks generic questions that don’t reference the student’s actual work. | Ensure file upload text extraction is working. Coach reviews Phase 1 questions in first week. Tune prompts if needed. |
| Inaccurate skill tags | Wrong tags distort coverage metrics and narrative content. | Students confirm/edit tags post-conversation. Coach reviews tags weekly. Track edit patterns to improve auto-tagging prompts. |
| LLM cost overruns | Unexpected costs from high conversation volume or narrative regeneration. | Monitor costs daily in first week. Gemini via NLU contract may be lower cost. Set up cost alerts. Cache narratives. |
| Auth/onboarding friction | Students can’t log in, magic links go to spam, onboarding confusing. | Test with 2 students before full launch. Provide clear email instructions. Have coach available for first-session support. |
| Data privacy concerns | Students or administration uncomfortable with AI processing reflections. | Document data handling: Supabase RLS isolates student data. LLM providers have enterprise data agreements. No PII beyond first name in prompts. |
| Gemini quality gap | Gemini produces lower quality questions/synthesis than Claude. | Run 10 conversations on both models before pilot. Score on specificity, warmth, and relevance. Use whichever scores higher. Can switch via env var. |